## Slide 1
December Case for Quality Forum
Dec 8, 2015
Ann Ferriter
Advanced Analytics for Medical Device Quality

## Slide 2: Charter
.
Problem Description | Stakeholders require accurate and complete data to make educated decisions to improve patient access to high quality devices. Three significant challenges to data on medical device quality: Lack of unbiased, relevant and available data No consistently applied performance measures and analytical methods No secure process or operating model to enable and encourage individual companies to be fully transparent about product quality. | 
Objective | To provide information and analysis techniques to stakeholders regarding medical device quality and subsequent patient value | 
Project Scope | Included | Excluded
 | Phase 1 Use case definition: Value Analysis Team and decisions regarding purchasing devices with defined device areas Use case development: conversion of data to information, create a set to validate Use case pilot and operating model options: identify benefits, identify what it would take to make into a working model | Not all stakeholders will be included in Phase 1 - Phase I will focus on Value Analysis teams. Future expansions could consider Group Purchasing Organizations, Payers, Healthcare professionals, patients, industry, etc.

## Slide 3: Team members
Joanna
Engelke
Boston Scientific
joanna.engelke@bsci.com
Steering Committee Sponsor
Project Manager
Project Leader
Rahmat
Muhammad
Deloitte & Touche LLP
rmuhammad@deloitte.com
Garth
Conrad
Medtronic - Spinal
garth.conrad@medtronic.com
Ann
Ferriter
FDA
Ann.Ferriter@fda.hhs.gov
Mike
Schiller
AHRMM
mschiller@aha.com
Danqing
Yu
Deloitte & Touche LLP
danqyu@deloitte.com
Rachael
Marshall
Deloitte & Touche LLP
ramarshall@deloitte.com
Jacqueline
Berretta
J&J - ASP
jberret@ITS.JNJ.com
Jeff
Kaser
J&J - Depuy
jkaser@ITS.JNJ.com
Nathan
Soderborg
Exponent
nsoderborg@exponent.com
Melissa
Lalomia
Stryker
melissa.lalomia@stryker.com
Daniel
Matlis
Axendia
dmatlis@axendia.com
George
Serafin
Deloitte & Touche LLP
gserafin@deloitte.com
Project Leader

## Slide 4
Voice of Customer

## Slide 5: VoC: factors that impact purchase decisions
Finance
Quality
Patient and clinician satisfaction
Participants identified three factors that impact purchase decisions:
Safety
Effectiveness
Reliability
Patient Experience
Usability
  Clinician satisfaction
Availability
Compatibility
Participants confirmed that the proposed quality categories are relevant to the purchase decision but indicated that reliable information is scarce.
Quality categories:

## Slide 6: VoC: willingness to participate in a pilot
All participants are willing to participate in a pilot. However, they require clarity on scope and requirements for them to share information.
Orlando Health
Providence Health & Services
VA
Baptist Health
Kettering Health Network
UAB Hospital

## Slide 7
Quality Categories

## Slide 8: Proposed quality categories: Safety and Effectiveness
Quality category | Proposed definition
Safety | Medical devices should be designed and manufactured in such a way that, when used under the conditions and for the purposes intended and, where applicable, by virtue of the technical knowledge, experience, education or training of intended users, they will not compromise the clinical condition or the safety of patients, or the safety and health of users or, where applicable, other persons, provided that any risks which may be associated with their use constitute acceptable risks when weighed against the benefits to the patient and are compatible with a high level of protection of health and safety. Essential Principles of Safety & Performance of Medical Devices GHTF (SG1-N020R5) June 30, 1999
Effectiveness | A device is clinically effective when it produces the effect intended by the manufacturer relative to the medical conditions … Effectiveness can be thought of as efficacy in the real world clinical environment. MEDICAL DEVICE REGULATIONS, Global overview and guiding principles

## Slide 9: Additional proposed quality categories
Quality category | Proposed definition
Reliability | Device will perform satisfactorily for a specified period of time under stated use conditions.
Patient Satisfaction | Patient’s perception that a device met or exceeded expectations of usability and outcome.
Usability | A characteristics of the device or device user interface that facilitates use and thereby establishes effectiveness, efficiency and user satisfaction in the intended use environment.
Availability | Device is available to fill first request orders.
Compatibility | If the device is intended for use in combination with other devices or equipment, the whole combination, including the connection system should be safe and should not impair the specified performance of the devices. Any restrictions on use applying to such combinations should be indicated on the label and/or in the instructions for use. Essential Principles of Safety and Performance of Medical Devices, FDA, GHTF/SG1/N41R9:2005
Note: These definitions are appropriate for the Analytics pilot. The definitions may evolve as a wider variety of devices bring added complexity to the terms.

## Slide 10: Sources of information about product quality
Pooled data from Value Analysis Teams
Registry data
Clinical trial data
FDA Adverse Events (MAUDE, SUS)
FDA R&L, 510(k), PMA
MedSun Reliability information
  Maintenance Logs
  Hospital Risk Management
Patient survey information
Clinician input on usability
Product specifications and reference to Standards

## Slide 11
Pilot Plan

## Slide 12: Activities to pilot launch
Define hypothesis
Define quality categories, metrics and data sources
Identify participants (Value Analysis Committees)
Identify device types for the pilot
Develop dashboards
Draft communications to pilot participants, including roles and responsibilities
Share dashboards with VACs, update based on feedback
Analyze VAC use of information
Finalize recommendations for analytics in medical device quality (include recommendations for operating model)

## Slide 13: Phase 1: Value Analysis Committee Purchasing Hypothesis
If VACs had access to the following information about implanted cardiac and orthopedic device performance:
Safety
Effectiveness
Reliability
Patient experience
Usability
Availability
Compatibility
and they applied predictive analytics to this information, then they would make better informed purchasing decisions to improve patient access to high quality medical devices.

## Slide 14: Device type for the pilot
Low interest
Medium
High interest
Implants
(stents, surgical mesh, pacemakers, defibrillators, large joints, spine)
Commodities
(ventilators, infusion pumps), Neuroembolization
Cardiac catheters
Device areas selected for pilot: Knees and Defibrillators

## Slide 15: Pilot Timeline
Key Activities and Dates | 
Pilot Activities | Dates
Develop dashboards | 20 Nov to 8 Jan 16
Identify data to be pooled from hospitals | 14 Dec to 4 Jan 16
Draft pilot participant roles and pilot expectations | 14 Dec to 4 Jan 16
Share dashboards with Value Analysis Teams and request participation Device areas: Knees and Defibrillators Quality criteria: Safety, Effectiveness, Usability, Availability, Reliability and Compatibility | 11 Jan 16
Identify pilot participants Goal 3 Value Analysis Teams | 15 Jan 16
Pilot use of quality information with Value Analysis Teams Gather feedback on 6 purchasing decisions | 30 Jan 16 to 30 Mar 16
Analyze results and draft recommendation | 31 Apr 16
Pilot Goal: Determine whether device quality information can be used effectively in Value Analysis Team purchasing decisions

## Slide 16: Illustrative Example
Chart: 
| Safety rating | Usability rating | Availability rating | Durability rating | Compatability rating | Customer satisfaction rating
Device 1 | 0.6 | 0.7 | 0.8 | 0.7 | 0.5 | 0.5
Device 2 | 0.6 | 0.5 | 0.3 | 0.7 | 0.5 | 0.4
Device 3 | 0.7 | 0.8 | 0.8 | 0.8 | 0.4 | 0.9
Device 4 | 0.6 | 0.7 | 0.8 | 0.65 | 0.5 | 0.7
Device 1
Device 2
Device 3
Device 4

## Slide 17
Status and Timeline

## Slide 18: MDIC Analytics Project status: 8 Dec 2015
Key Deliverables / Milestones |  |  | 
Milestones / Deliverable | Dates | Percent Complete | Status
Prepare and approve charter | 25 Sep 15 | 100% | 
Form hypothesis | 09 Oct 15 | 100 % | 
Interview Value Analysis teams | 10 Nov to 20 Nov 15 | 100 % | 
Identify quality characteristics, metrics, data sources | 20 Nov 15 | 100 % | 
Select device areas | 20 Nov 15 | 100 % | 
Develop and share pilot proposal at CfQ forum | 7 Dec 15 | 100% | 
Develop dashboards | 20 Nov to 8 Jan 16 | 0% | 
Identify pilot participants | 15 Jan 16 | 0% | 
Pilot prep | 15 Jan 16 | 0% | 
Pilot use of Quality information with Value Analysis Teams | 30 Jan 16 to 30 Mar 16 | 0 % | 
Analyze results and draft recommendation | 31 Apr 16 | 0% | 
G
Y
R
= On Time
= At Risk
= Late
C
= Complete
Results / Accomplishments
Interviewed Value Analysis Teams including: UAB Hospital, Birmingham AL, Baptist Health, Little Rock, AR, Kettering Health Network, Miamisburg, OH, Orlando Health, Orlando, FL, VA NCPS, Ann Arbor, MI, Providence Health & Services Seattle, WA Identified sources of information on Safety, Effectiveness, Usability, Availability, Reliability and Compatibility Selected knees and defibrillators as pilot device areas.
Upcoming Activities | 
Activity | Target Date
Create dashboards with Safety, Effectiveness, Usability, Availability, Reliability and Compatibility information on knees and defibrillators | 8 Jan 16
Draft detailed pilot plan | 15 Jan 16
Draft advanced analytics agenda for CfQ forum December 8th in Washington, DC | 7 Dec 15
Issues/Risks | Mitigation
Aggressive timeline Need resources to develop dashboards | Requesting resources Request to pool data from Value Analysis teams
C
C
G
G
G
G
Y
C
C
C
C

## Slide 19: Project timeline and milestones
 | September 2015 |  |  |  | October 2015 |  |  |  | November 2015 |  |  |  | December 2015 |  |  |  | January 2016 |  |  |  | February 2016 |  |  |  | March 2016 |  |  |  | April 2016 |  |  | 
Timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pilot Development
Present project plan and initial voice of customer data at CfQ Forum
Use Case Definition
Conduct Pilot
    Gather additional information to refine hypothesis, quality characteristics, and feasibility of obtaining
Develop mock dashboards for agreed-upon quality characteristics
Present pilot plan at CfQ Forum
Pilot kickoff
Finalize quality characteristics, metrics and data sources and propose pilot plan
Develop recommendations for operating model
Form hypothesis (what are we trying to get out of the data?)
Prepare and Approve Charter
Identify three (3) pilot participants
Pilot prep

## Slide 20
Questions?